## PCB-Norm
Genaral Information
|  | Author | Quality Accounting
|  | Receiver | BOM and SEPG
|  | From date | 2013-06-01
1) | Objectives
Process Capability Baseline are measurement of Performance for the organization's set of standard processes at various levels of details as appropriate
2) | Scope
Production data and metrics of all Fsoft projects in the period of S2-2013
3) | References
Fsoft Quality Plan 2013
QPPO
4) | Data sources
- The source of data is the Software Process Database which collects the data from project database stored in project records and Fsoft Management Suites (Fsoft Insight, Timesheet and DMS). Those have been inspected and approved by QA.Accounting
5) | Assumption
- Some projects are not included in the metric calculation and analysis of selected metrics because they have been cancelled by customers, their project life cycle is very specific ("Other type"), or their data are not adequacy for analysing those.
- Some projects have applied specific tailoring/deviation that impacts the performance data
- Successfulness of PPM implementation is not included in this PCB
6) | Statistical techniques applied and models used
Control chart, Scatter Plot, Histogram, Normality test, 2 sample-t test, ANOVA, F-test,…
7) | Calculate Control Limits (LCL, UCL) and Specification limit (LSL, USL)
The control limits have been set to maintain Fsoft quality system in quantitative control, and give the goals for improvement.
The UCL and LCL for the metrics are set based on the:
- The average (represented as A) of
- Standard Deviation (represented as B)
UCL = A + 3B
LCL = A - 3B
Fsoft Norm could be reached by adjustment suggested Specification limit. Those are calculated as below:
When B < 15% of A then,
USL = A + 3B
LSL = A - 3B
When B < 25% of A then,
USL = A + 2B
LSL = A - 2B
When B < 50% of A then,
USL = A + B
LSL = A - B
When 50% of the A <= B < A then,
USL = A + 0.5B
LSL = A - 0.5B
When B >= A then variability of the data population is considered as very high.
When A is used for measuring a deviation, the A'=A+1 is used instead A for calculating K (K=B/A')
The projects with metrics caused by reasons beyond our process control (so-called extraordinary reason), will be removed
The adjustment could be based on improvement rate expected by Fsoft organization and the Capability Analysis
8) | Metric list
| No | Name | Unit | PCB 28 |  |  | Norm S1-2014
|  |  |  | LCL | Average | UCL | LSL | Target | USL
Quality Objectives
| 1 | Leakage TS | Wdef/MM | 0 | 0.1718 | 1.2055 | 0 | 0.32 | 0.63
|  | Development |  | 0 | 0.23986 | 1.4967 | 0 | 0.3 | 0.8
|  | Maintenance |  | 0 | 0.094914 | 0.64425 | 0 | 0.2 | 0.4
|  | Test |  | 0 | 0.014499 | 0.1066 | 0 | 0.015 | 0.1
|  | Migration |  | 0 | 0.20339 | 1.022 | 0 | 0.4 | 0,8
|  | Others |  | 0 | 0.088229 | 0.68603 | 0 | 0.10212 | 0.22693
| 2 | Customer satisfaction | Point | 48.8402 | 86.7831 | 100 | 80 | 84 | 90
| 2.1 | CSS Conversion | Point | 43.2708 | 83.2331 | 100 | 78 | 82 | 88
|  | Japan Market converted rate |  |  | 1 |  |  | 1
|  | Non Japan Market converted rate |  |  | 0.91 |  |  | 0.9
| 3 | Project productivity | LOC/pd | 0 | 87.3469 | 479.8223 | 44.9836 | 89.9673 | 134.9509
|  | Development |  | 0 | 84.0389 | 413.7486 | 43.2801 | 86.5601 | 129.8402
|  | Maintenance |  | 0 | 69.1155 | 368.0852 | 35.5945 | 71.189 | 106.7834
| 3.1 | By project scope
| 3.1.1 | C-UT |  | 0 | 175.302 | 774.0266 | 90.2805 | 180.561 | 270.8416
| 3.1.2 | C-Test |  | 0 | 81.2225 | 291.9237 | 41.8296 | 83.6591 | 125.4887
| 3.1.3 | D-C-Test |  | 0 | 62.274 | 293.12 | 57.728 | 64.1423 | 70.5565
| 3.1.4 | Others |  | 0 | 66.465 | 286.0627 | 61.6131 | 68.459 | 75.3049
| 3.2 | By Programing language
| 3.2.1 | Java language |  | 0 | 50.3782 | 158.2197 | 25.9448 | 51.8896 | 77.8343
| 3.2.2 | C# language |  | 0 | 81.744 | 388.6931 | 42.0982 | 84.1964 | 126.2945
| 3.2.3 | Cobol language
| 3.2.4 | C++ language |  | 0 | 86.8396 | 397.5791 | 44.7224 | 89.4448 | 134.1671
| 3.2.5 | C language |  | 0 | 82.599 | 345.0911 | 76.5693 | 85.077 | 93.5847
|  | Coding Productivity |  | 0 | 203.7389 | 749.4562 | 104.9255 | 209.8511 | 314.7766
|  | Development |  | 0 | 210.1171 | 783.6904 | 108.2103 | 216.4207 | 324.631
|  | Maintenance |  | 0 | 178.0718 | 479.8223 | 91.707 | 183.4139 | 275.1209
| 4 | Timeliness | % | 76.4787 | 97.4541 | 100 | 91 | 96 | 100
|  | Development |  | 74.6088 | 97.3581 | 100 | 90 | 95 | 100
|  | Maintenance |  | 76.7085 | 97.309 | 100 | 96 | 98 | 100
|  | Test |  | 87.6553 | 98.5456 | 100 | 96 | 98 | 100
|  | Migration |  | 69.0974 | 96.3736 | 100 | 96 | 98 | 100
|  | Others |  | 69.1672 | 96 | 100 | 96 | 98 | 100
| 5 | Effort Efficiency | % | 41.5744 | 95.4275 | 149.2805 | 85 | 90 | 95
|  | Development |  | 28.9629 | 93.2783 | 157.5937 | 83 | 88 | 93
|  | Maintenance |  | 41.3907 | 97.3456 | 153.3005 | 85 | 90 | 95
|  | Test |  | 52.2572 | 98.2568 | 144.2565 | 87 | 92 | 97
|  | Others |  | 26.1467 | 90.2098 | 154.2729 | 83 | 88 | 93
|  | Migration |  | 21.9222 | 106.836 | 191.7498 | 93 | 98 | 103
| 6 | Unit Effort Efficiency |  |  | 73.752 |  |  | 75
Process performance indicator
Quality
| 6 | Defect Rate | Wdef/MM | 0 | 18.0011 | 74.2198 | 15 | 20 | 25
|  | Development |  | 0 | 24.1763 | 88.27 | 20 | 25 | 30
|  | Maintenance |  | 0 | 14.049 | 50.306 | 12 | 17 | 22
|  | Test |  | 0 | 4.0614 | 22.9576 | 3 | 6 | 9
| 7 | Defect Removal Efficiency | % | 52.9173 | 91.6488 | 100 | 90 | 95 | 100
|  | Development |  | 70.7457 | 94.6434 | 100 | 90 | 95 | 100
|  | Maintenance |  | 30.8676 | 84.7668 | 100 | 85 | 90 | 95
|  | Test |  | 48.9916 | 91.8797 | 100 | 88 | 90 | 100
| 8 | Review Efficiency | % | 0 | 48.2439 | 100 | 45 | 50 | 55
|  | Development |  | 0 | 41.7544 | 100 | 40 | 45 | 50
|  | Maintenance |  | 0 | 48.7318 | 100 | 45 | 50 | 55
| 9 | Test Efficiency | % | 0 | 40.1551 | 100 | 45 | 50 | 55
|  | Development |  | 0 | 52.1634 | 100 | 45 | 50 | 55
|  | Maintenance |  | 0 | 34.353 | 100 | 40 | 45 | 50
Cost
| 10 | Correction Cost | % | 0 | 6.052 | 20.8191 | 3 | 5 | 7
|  | Development |  | 0 | 8.1687 | 23.7878 | 4 | 6 | 8
|  | Maintenance |  | 0 | 4.3271 | 13.9763 | 2 | 4 | 6
|  | Test |  | 0 | 1.7603 | 8.9396 | 0.5 | 1 | 1.5
|  | Migration |  | 0 | 6.468 | 16.8237 | 3 | 5.5 | 8
|  | Others |  | 0 | 3.4266 | 12.877 | 1 | 1.5 | 2
Note on C64: Project LOC/Total project effort
Note on C71: S-D-C-Test and S-C-Test
Note on C78: Project LOC/Effort of coding