## Risk_Management
Total | No | Risk Description | Category | Root Cause | Risk Owner | Impact | Mitigation Solution | Status Of Risk | Market Risk | Open
| 1 | Developer of project doesn't have any experience about PHP language and unit test for PHP. | Technology Risk | Developer has not worked or studied with PHP language before. | CuongNM,HoangLH,CuongPH,LinhNT | - Project may be late not as schedule. Because developer must spend much time to study PHP Language. | - Have plan for developer to study and code demo by PHP language before the project start. - Refer unit test of Fsoft's project. | Occurred | Financial Risk | Occurred
| 2 | Developer of project doesn't have experience about design website by PHP language. | Technology Risk | Developer has not worked or studied with PHP language before. | CuongNM,HoangLH,CuongPH,LinhNT | - Project may have poor or wrong design. | - Due to CuongNM has experience with Photoshop and CuongPH has experience with css/html design,so it'is not hard to design with PHP. - Refer good design website that concern with requirement. Example : "http://timhong.vn/vi","http://www.nihbt.org.vn/".... | Occurred | Technology Risk | Closed
| 3 | Tester of project may can't join with project full time. | People Risk | Tester must work in SamSung Company fulltime. | TamNT | - Website may not be tested clearly and fully. | - TamNT will join full time in project when it is necessary. | Occurred | People Risk
| 4 | FPT University request we must write report by Japanese but we don't have enough experience to do. | Technology Risk | Not yet | LinhNT | - If won't have good report version Japanese, may get low mark. | - We will improve knowleage about IT Japanese and get support from Comtor in Fsoft. | Occurred | Structure/Process Risk
| 5 | During the time doing project, member of project may have problem and can't do their job fully. | People Risk | Not yet | All member | - Their job may be late and affect project schedule. | - Always have the people to support for another when it is necessary | Open
Total | 5

## Issue_Management
No | Issue Description | Category | Root Cause | Issue Owner | Impact | Mitigation Solution | Status
1 | Developer of project doesn't have any experience about PHP language and unit test for PHP. | Technology | Developer has not worked or studied with PHP language before. | CuongNM,HoangLH,CuongPH,LinhNT | - Project may be late not as schedule. Because developer must spend much time to study PHP Language. | - Have plan for developer to study and code demo by PHP language before the project start. - Refer unit test of Fsoft's project. | Open | Open | Market
2 | Developer of project doesn't have experience about design website by PHP language. | People | Developer has not worked or studied with PHP language before. | CuongNM,HoangLH,CuongPH,LinhNT | - Project may have poor or wrong design. | - Due to CuongNM has experience with Photoshop and CuongPH has experience with css/html design,so it'is not hard to design with PHP. - Refer good design website that concern with requirement. Example : "http://timhong.vn/vi","http://www.nihbt.org.vn/".... | Open | Closed | Financial
3 | Tester of project may can't join with project full time. | People | Tester must work in SamSung Company fulltime. | TamNT | - Website may not be tested clearly and fully. | - TamNT will join full time in project when it is necessary. | Open |  | Technology
4 | FPT University request we must write report by Japanese but we don't have enough experience to do. | Technology | Not yet | LinhNT | - If won't have good report version Japanese, may get low mark. | - We will improve knowleage about IT Japanese and get support from Comtor in Fsoft. | Open |  | People
Structure/Process