## Quality Report
Quality Report
# | Product | Quality Control Activity | Defect (No of Def/KLOC)
|  |  | Plan | Actual
1 | Test case | Unit Test | 3-4(DP/KLOC) | 18
|  | Component Test | 3-4(DP/KLOC) | 16
|  | Integration Test | 2-3(DP/KLOC) | 9
|  | System Test | 4-6(DP/KLOC) | 13
|  | Leakage (UAT) | 1-2
2 | Requirements | Review | 10 | 6
3 | Design | Review | 15 | 21
4 | Code | Review | 30 | 15
5 | Project Plan | Review | 10 | 3
6 | Project Schedule | Review | 10 | 6
7 | Test Plan | Review | 10 | 4
8 | Other document | Review | 15 | 10
Total |  |  |  | 121