## WBS Estimation
# | WBS Item | % | KLOC | Effort (Man-day) | Cost ($)
1 | Requirements | 18% |  | 26.2286 | 1836
2 | Design | 15% |  | 21.8571 | 1092.8571
3 | Coding & Unit Test | 35% |  | 51 | 2040
3.1 StaffManagement
UI-Screen(JSP/Servlet)
| Search Staff |  | 1.5 | 5
| Add New Staff |  | 1 | 3.3333
| Edit Staff |  | 1.5 | 5
BusinessLogic (Java)
| StaffBusiness Classes |  | 2 | 13.3333 |  | Metrics
| 3.2 Admin |  |  |  |  | Item | Productivity | Unit
| UI-Screen(JSP/Servlet) |  |  | 0 |  | JSP/Servlet | 0.3 | KLOC/Man-day
| Search User |  | 1 | 3.3333 |  | Java | 0.15 | KLOC/Man-day
| Add New User |  | 0.8 | 2.6667 |  | PM | 100 | $/man-day
| Edit User Profile |  | 1.5 | 5 |  | Test | 50 | $/man-day
| BusinessLogic (Java) |  |  |  |  | DEV | 40 | $/man-day
| AdminBusiness Classes |  | 2 | 13.3333 |  | Designer | 50 | $/man-day
4 | Testing | 23% |  | 33.5143 | 1675.7143 | BA | 70 | $/man-day
5 | Deployment (customer support) | 2% |  | 2.9143 | 116.5714
6 | Project Management | 7% |  | 10.2 | 1.53
| Total | 100% | 11.3 | 145.7143 | 6762.6729